## Change Request Log
Change Request Id | Date submitted | Submitted by | Description | Reason/Justification | Impact Analysis | Priority | Approval Status | Approved by & date
1 | 12-Jun-26 | Exam Controller | Online exam registration module for students | Reduce paperwork, reduce queues, don't visit university as in person for registration | Core module, need database, login/signup UI, EXAM REGISTRATION form UI. | HIGH | Approved | Project Manager 13-June-2026
2 | 11-Jun-26 | Project Manager | Need Admin dashboard, generate report for students grade, download/export excel format. | Admin/exam controller needs reports without IT help. | Admin Dashboard, export, download Business logic. | Medium | Approved | Project Manager 13-June-2026
3 | 2026-06-12 | Student Affairs | Auto-generate and email roll number slips as PDF | Students waste days waiting in lines to collect slips. | PDF library needed. Email server config required. | Medium | Approved | Project Manager 07-Apr-2025
4 | 2026-06-15 | Finance Dept | Add penalty fee auto-calculation for late registration | Manual penalty calculation causes errors and disputes. | Small logic change in payment module. | Low | Pending | Under Review